## Sheet1
Story | Conditions | Assumptions | Sprint 2 Test Pass/Fail | Sprint 3 Test Pass/Fail | Sprint 4 Test Pass/Fail | Comments on process / results | Tested By: | Tested On:
Example 1- Login | (not all stories will have a happy/unhappy format) Happy Path: Login data entered. Data is correct. Successful login message sent. Welcome page loaded. Unhappy Path: Login data entered. Data is incorrect. Unsuccessful login message sent. Login page reloaded. | [5 empty] | Kisenge Mbaga | 2021-10-12
Sprint 2
Student Cohort | Given, a student started in SJ in Sept 2017, When a student is viewed in a list there cohort is displayed as 2017-18SJ. | Data is uploaded and handled properly | Pass | Pass | Pass |  | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
| Given, a student started in FR in Jan 2017, When a student is viewed in a list there cohort is displayed as 2016-17FR. | Data is uploaded and handled properly | Pass | Pass | Pass |  | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
View Transcript | Given, when the user clicks a student from the student list then, it should pop up the transcript of the selected student. | Data is uploaded and handled properly | Pass | Pass | Pass |  | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
| Given, when the user displays the transcript, then it should have student details <student name, student ID, cohort, rank> and course details<course number, course name, course grade, course term and section, course type>. | Data is uploaded and handled properly | Pass | Pass | Pass |  | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
| Given, when the user wants to sort transcripts then, it can be done by <course, term, type, and grade>. | Data is uploaded and handled properly | Pass | Pass | Pass | Can be sorted by: Course ID Title, Grade, Term, Section, Credit Hours, Type, Passed | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
View Detailed List of Students | Given that a user has a valid set of data when they uploaded it then a list of students is displayed. | Data is uploaded and handled properly | Pass | Pass | Pass |  | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
| Given that student: 5625655 Abigail Hays F 1-772-555-4565 515 Lower River Avenue Merrimack, NH 03054 AHAYS BSSWE FR 2019-09-01 is in personData.txt when that data is uploaded then the following must be displayed in the list. 2019-20FR HaysA 5625655 <Rank> <Status> | Data is uploaded and handled properly | Pass | Pass | Pass | Displayed as: 5625655 HaysA 2019-20FR <Rank> <Status> | Grace | 2021-10-27 | 2021-11-17 | 2021-12-01
Sprint 3
Organize Students by Rank | Given, when the user is the program coordinator, then the user must click on the PC icon in the sidebar to access the ranks list. |  |  | Fail | Fail | not implemented on side bar | Grace |  | 2021-11-17 | 2021-12-01
| Given, when the user is the program coordinator who wants to access the student ranks list, then data should be displayed on the same window. | Data is uploaded and handled properly |  | Pass | Pass | listed on main student page | Grace |  | 2021-11-17 | 2021-12-01
| Given when the student ranks are displayed then it should be processed with the help of credit hours or prerequisites. | Data is uploaded and handled properly |  | Pass | Pass | Calculate Rank Dropdown | Grace |  | 2021-11-17 | 2021-12-01
Print Transcript | Given a user is on a student transcript, when they click export, then they can print the transcript | Data is uploaded and handled properly |  | Pass | Pass | added this uat to the story on sprint 3 board | Grace |  | 2021-11-17 | 2021-12-01
| Given a user is on a student transcript, when they click export, then they can download the transcript | Data is uploaded and handled properly |  | Pass | Pass | added this uat to the story on sprint 3 board | Grace |  | 2021-11-17 | 2021-12-01
Delete Files | Given a user is logged in and would like to remove a data set, when the 'extras menu' button is clicked followed bny 'delete files', a confirmation pops up to confirm you want to delete the current data set is deleted, then when confirm is clicked, the dataset is deleted | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
Login Page | Given the user arrives to the site, when the user enters the login credentials, then they are logged in and arrive to the home page |  |  | Pass | Pass | user & pass: admin | Grace |  | 2021-11-17 | 2021-12-01
| Given the user arrives to the site, when the user enters incorrect login credentials, then they are not logged in |  |  | Pass | Pass | added this uat to the story on sprint 3 board, error message pops up | Grace |  | 2021-11-17 | 2021-12-01
Logout | Given the user is logged in, when the logout button is clicked, then the user is logged out and is on the home page | User is logged in |  | Pass | Pass | added this uat to the story on sprint 3 board | Grace |  | 2021-11-17 | 2021-12-01
List Count by Campus | Given, when the user uploads the required data, then the total number by rank students should always be displayed. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
| Given when the user views the table, the table should have ranks (FIR, SOP.JUN, SEN ), and each individual count, and the total number of students in the program. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
List Count by Co-Op | Given, when the user uploads the required data, then the total number of Co-op students should always be displayed. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
| Given, when the user views the list count by the co-op, then the data should be displayed in matrix format and the table should have Co-op and the total number of students. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
List Count by Rank | Given when the user views the table, the table should have ranks (FIR, SOP.JUN, SEN ), and each individual count, and the total number of students in the program. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
| Given, when the user uploads the required data, then the total number by rank students should always be displayed. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
| Given when the user views the table, the table should have ranks (FIR, SOP.JUN, SEN ), and each individual count, and the total number of students in the program. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  | Pass | Pass |  | Grace |  | 2021-11-17 | 2021-12-01
Sprint 4
Audit Basic Science Courses | Given, when the user clicks a student from the student list then, it should pop up the audit of the selected student in text or matrix format. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  |  | Pass |  | Grace |  |  | 2021-12-01
| Given, when the user wants to edit the BAS SCI course tags then, it must be specified for the user to edit (Ex. 'BIOL', 'PHYS', 'CHEM', 'ESCI', 'APSC', 'ASTR'); should also be able to specify exclusions (EX APSC1082). | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  |  | Pass |  | Grace |  |  | 2021-12-01
Audit Core Courses | Given, when the user clicks a student from the student list then, it should pop up the audit of the selected student in text or matrix format. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  |  | Pass |  | Grace |  |  | 2021-12-01
| Given, when the users need to be able to specify replacements then, the user can view and select the CORE courses are specified precisely in the program matrix | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  |  | Pass |  | Grace |  |  | 2021-12-01
List Count By Course | Given when the user clicks the button to view the course list, then it should display the table in matrix format. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  |  | Pass |  | Grace |  |  | 2021-12-01
| Given, when the user views the list count by the courses, then the data should be displayed in matrix format and the table should have different courses and the total number of students in each individual course. | User is logged in and on the correct page, and there are files uploaded. Data is uploaded and handled properly |  |  | Pass |  | Grace |  |  | 2021-12-01